## Distribution
Sr.# | Project Name | Total Scope DC | As-builts Received | Percentage of Work Completed | Status
1 | Bahria Phase 8 Sector B | 25 DC | 25 DC | 100% | Updated
2 | Bahria Phase 8 Sector C | 23 DC | 23 DC | 100% | Updated
3 | Bahria Phase 8 Sector D | 22 DC | 12 DC | 55% | Not Updated
4 | Bahria Phase 8 Sector F-8/2 | 41 DC | 30 DC | 73% | Not Updated
5 | Bahria Phase 8 Sector F-8/3 | 33 DC | 10 DC | 30% | Not Updated
6 | BahriaPhase 8 Overses 3 | 10 DC | 0 DC | 0% | Not Updated
7 | Bahria Phase 8 Overses7 | 8 DC | 0 DC | 0% | Not Updated
8 | DHA-4 | 51 DC | 23 DC | 45% | Updated
9 | H-13 | 8 DC | 0 DC | 0% | Not Updated
10 | PWD | 4 DC | 4 DC | 100% | Updated
11 | G-8 Markaz | 11 DC | 11 DC | 100% | Updated
12 | I-8/4 | 23 DC | 0 DC | 0% | Not Updated
13 | I-10/1 | 22 DC | 0 DC | 0% | Not Updated

## Feeder
Sr # | Project Name | Total Scope (km) | As-builts Received | Percentage of Work Completed | Status
1 | Bahria Ph 7 POP Ring Project | 6 (km) | 6 (km) | 100% | Updated
2 | DHA -CSC POP to Bahria 8 POP Via Sereen City (BH 7) | 11 (km) | 11 (km) | 100% | Updated
3 | Railway Back Haul | 52 (km) | 16 (km) | 31% | Not Updated
4 | H-13 | 10 (km) | 10 (km) | 100% | Updated
5 | New Blue Area | 14 (km) | 14 (km) | 100% | Updated